## Sheet1
Item | P | I | Risk (P*I) | Recognized | Mitigated/ Resolved | ROAM | How
Physics engine does't work | 8 | 100 | 800 | 2023-03-24 | Accepted | A | Projectiles won't exist for very long so the small energy losses over time would not affect anything in a serious way. If something else crops up that exasterbates this issue then it can become another item
ITC doesn't work as expected | 8 | 40 | 320 | 2023-03-24
I don't have enough time to work on project and I fall behind | 8 | 70 | 560 | 2023-03-24 | Mitigated | M | More precise time-management will be employed and weekly checkins will keep me accountable
Time estimates are lower than the time spent | 70 | 13 | 910 | 2023-03-24 | Mitigated | M | I increase time estimate values and adjust schedule accordingly. RTOS > partying
Graphics take too long to create | 20 | 13 | 260 | 2023-03-24 | Resolved | R | Making the first few macros took very little time and the method I have for it is fast for prototyping and fine-tuning.
I require over 100% CPU util to accomplish goals | 2 | 70 | 140 | 2023-03-24
Physics engine take too long to debug | 3 | 40 | 120 | 2023-03-24 | Resolved | R | The method I am using of divying up the physics task into different sub-systems is working well.
Data structures don't hold data / perform as expected | 8 | 20 | 160 | 2023-03-24
Test Ball doesn't have constant energy | 100 | 1 | 100 | 2023-04-06 | Accepted | A | Projectiles won't exist for very long so the small energy losses over time would not affect anything in a serious way. If something else crops up that exasterbates this issue then it can become another item
Physics and display tasks timers aren't fast enough | 40 | 40 | 1600 | 2023-04-06
Project specifics aren't in line with my implementations and would take to long to pivot | 5 | 13 | 65 | 2023-04-13

## Sheet2
Valid Modified Fibonacci values
1
2
3
5
8
13
20
40
70
100